## Sample Project Plan (Rev)
Migration Sample Project Plan (Platform)
This sample project plan defines the high-level steps and suggested timelines for migrating one or more applications to a new RTL in Pega Cloud. Use this template as a guide to formulate your own migration plan that addresses all the tasks required for a successful migration. If migrating into an existing RTL or performing a staged migration, additional steps are required. If migrating a CDH Application, see the Sample plan specific to CDH because the process is different. Legend: x - planned (blue) a - overdue (amber) b - blocked (red) c - complete (green) ** Denotes Optional tasks Optional tasks might be required depending on the specifics of the migration. If a task is required for your project, determine the duration and extend the timeline accordingly. Common optional tasks are parallel development, SFTP provisioning, and production mirror environment setup. There might be other optional tasks.
Migration Step | Responsibility | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Stage 1: Assessment and Planning (NOTE: Some tasks may be completed during the sales and discovery process) | bar: Week 1 to Week 2
Review the migration documentation, tools, and resources provided by Pega | Client | bar: Week 1
Run the latest version of the Pega Cloud Readiness Tool | Pega/Client | bar: Week 1
Complete the Migration Gap Assessment Worksheet | Pega/Client | bar: Week 1
Review the Pega Cloud Readiness Tool output report and Gap Assessment Worksheet with the Pega team | Pega/Client | bar: Week 1
Identify gaps between the existing system (on-premises or client-managed cloud) and Pega Cloud | Pega/Client | bar: Week 1
Determine target architecture on Pega Cloud (RTLs, environments, connectivity, and required storage, etc.) | Pega/Client | bar: Week 1
Plan connectivity between existing systems and Pega Cloud (Pega Cloud data migration tools, SSO, integrations, SFTP, etc.) | Pega/Client | bar: Week 2
Create a plan to address all identified cloud readiness gaps | Client | bar: Week 2
Define a testing strategy (including: unit and regression, end-to-end, background processing, security & vulnerability, performance) | Client | bar: Week 2
Define a DevOps strategy | Client | bar: Week 2
Create a migration project plan | Client | bar: Week 2
Establish project governance and cadence | Pega/Client | bar: Week 2
Stage 2: Provisioning and Connectivity Setup (Connectivity can be performed in parallel with stage 3) | bar: Week 1 to Week 5
Complete client-side connectivity and networking setup | Client | bar: Week 1 to Week 3
Pega provisions environments on Pega Cloud | Pega | bar: Week 2
** Raise Cloud Change requests to establish connectivity (Such as Task Name: Network-AWS PrivateLink Connectivity Change or GCP Private Service Connect Ingress and Egress) | Client/Pega | bar: Week 3
Establish Pega Cloud connectivity (SSO, Integrations, SFTP, etc.) | Client/Pega | bar: Week 3 to Week 4
Perform testing to validate connectivity (SSO, Integrations, SFTP, etc.) | Client/Pega | bar: Week 4 to Week 5
Stage 3: Application Migration and Remediation (DT1) | bar: Week 3 to Week 5
Migrate application Rules via RAP file method from existing systems to Pega Cloud development environment | Client | bar: Week 3
Infinity '25 - Update Rules for Tomcat 10.1 compatibility - Run the Activity named pxQueueJavaEERuleUpdateUtility - Review PegaRULES.log file and validate modified Rules | Client | bar: Week 3
** Infinity '25 - Update custom JARs for Tomcat 10.1 compatibility (If required) **- Increment CodeSet and import Jakarta compatible custom JARs to new CodeSet. **- Restart instance | Client | bar: Week 3
Migrate associated test data from existing systems to Pega Cloud development environment via RAP file method. | Client | bar: Week 3
Configure integrations for testing (SSO, endpoint services, listeners, BIX, external DB connectivity, etc.) | Client | bar: Week 3
**Configure SFTP (If required) | Client | bar: Week 3
Address all post-migration cloud readiness gaps identified during Stage 1: Assessment and Planning | Client | bar: Week 3 to Week 4
Perform unit and regression testing | Client | bar: Week 4 to Week 5
Fix any issues found in testing | Client | bar: Week 4 to Week 5
Review the application using PDC | Client | bar: Week 5
Stage 4: Application Validation (STG1) | bar: Week 6 to Week 7
Promote application Rules from Pega Cloud development to Pega Cloud staging environment | Client | bar: Week 6
** Infinity '25 - Update custom JARs for Tomcat 10.1 compatibility (If required) **- Increment CodeSet and import Jakarta compatible custom JARs to new CodeSet. **- Restart instance | Client | bar: Week 6
Migrate associated test data via RAP file method from source systems to Pega Cloud staging environment | Client | bar: Week 6
Configure integrations for testing (SSO, endpoint services, listeners, BIX, external DB connectivity, etc.) | Client | bar: Week 6
**Configure SFTP (If required) | Client | bar: Week 6
Perform end-to-end application functional and integration testing | Client | bar: Week 6 to Week 7
Fix any issues found in testing | Client | bar: Week 6 to Week 7
**Merge parallel application development from source system to Pega Cloud development environment via RAP | Client | bar: Week 7
** Infinity '25 - Update Rules for Tomcat 10.1 compatibility (Required if merging parallel development to Pega Cloud development environment.) **- Run the activity named pxQueueJavaEERuleUpdateUtility ** - Review PegaRULES.log file and validate modified Rules | Client | bar: Week 7
** Perform end-to-end application functional and integration testing to validate parallel development changes | Client | bar: Week 7
Review the applications using PDC | Client | bar: Week 7
Run security tests (if not completed during application validation) | Client | bar: Week 7
Sign off on application readiness for production | Client | bar: Week 7
Freeze application code in Pega Cloud | Client | bar: Week 7
Stage 5: Data Migration Dry Run (PROD) | bar: Week 5 to Week 9
Complete pre-requisites for data migration See: https://docs.pega.com/bundle/migration-modernization/page/pega-cloud-migration-modernization/data-migration-prerequisites-summary.html | Pega/Client | bar: Week 5
Complete the Database Migration Artifact Sheet | Client | bar: Week 5
Raise Cloud Change request for data migration with a lead time of 2 weeks (Task Name: Onprem - Pega Cloud Migration Activity) | Client | bar: Week 5
Promote application Rules from staging to Pega Cloud production | Client | bar: Week 5
Test connectivity to source database and filesystem | Client/Pega | bar: Week 6 to Week 7
** Infinity '25 - Update custom JARs for Tomcat 10.1 compatibility (If required) **- Increment CodeSet and import Jakarta compatible custom JARs to new CodeSet. **- Restart instance | Client | bar: Week 5 to Week 6
**Configure SFTP (If required) | Client | bar: Week 6
Configure integrations (SSO, endpoint services, listeners, BIX, external DB connectivity, etc.) | Client | bar: Week 6 to Week 7
Export RAP file with all PROD DSS, configurations, and integration settings (They will be overwritten by the on-premises data.) | Pega | bar: Week 7
Migrate data from source system to Pega Cloud using data migration tooling | Pega | bar: Week 8
Validate data and perform post migration activities (Apply indexes, time zone correction, etc.) | Pega | bar: Week 8
Perform data update to latest Pega version | Pega | bar: Week 8
Perform application functional testing | Client | bar: Week 8
Run performance tests | Client | bar: Week 8 to Week 9
Perform PDC Review | Pega/Client | bar: Week 9
Remediate any issues | Client | bar: Week 9
Create Production Cutover Runbook | Pega/Client | bar: Week 8 to Week 9
Stage 6: Production Data Migration and Go Live | bar: Week 8; Week 10
Raise Cloud Change request for data migration with a lead time of 2 weeks (Task Name: Onprem - Pega Cloud Migration Activity) | Client | bar: Week 8
Export RAP file with all DSS, configurations, and integration settings from production (They will be overwritten by the on-premises data.) | Client | bar: Week 10
Follow the steps in the Production Cutover Runbook created during Data Migration Dry Run | Pega/Client | bar: Week 10
Have go/no-go decision meeting with all stakeholders | Pega/Client | bar: Week 10
When Migration is completed, direct users to new URLs | Client | bar: Week 10
Stage 7: Post Go-Live Support (HyperCare) | bar: Week 10 to Week 11
Pega monitors the Pega Cloud deployment | Pega | bar: Week 10 to Week 11
Review what went well and what could be improved in the future | Pega/Client | bar: Week 11